## Sheet1
Key ID's | Director | ADM | Team Name | Total | Onsite | Offshore | KT Start Date | KT End Date | CW ID | ADID | RSA | Citrix / Laptop | Knowledge Acquisition | Assisted Perform | Independent Perform | Steady State | Billing Start Date | Key Updates | Remarks
ProjectName_01 | Benjamin | Oliver | Team One | 3 | 0 | 3 | 2024-02-05 | 2024-03-05 | 3 | 3 | 3 | 3 | 2024-02-20 | 2024-02-27 | 2024-03-05 | 2024-03-06 | 2024-03-06 | KT Completed. In Steady State.
ProjectName_02 | Benjamin | Oliver | Team two | 2 | 0 | 2 | 2024-02-21 | 2024-03-28 | 2 | 2 | 2 | 2 | 2024-03-07 | 2024-03-21 | 2024-03-28 | 2024-03-29 | 2024-03-29 | KT Completed. In Steady State.
ProjectName_03 | Serenity Panickar | Noah | Team three | 3 | 0 | 3 | 2024-01-29 | 2024-03-15 | 3 | 3 | 3 | 3 | 2024-02-16 | 2024-03-01 | 2024-03-29 | 2024-04-01 | 2024-04-01 | KT Completed. In Steady State.
ProjectName_04 | Serenity Panickar | Noah | Team 4 | 1 | 1 | 0 | 2024-01-29 | 2024-03-15 | 1 | 1 | 1 | 1 | 2024-02-16 | 2024-03-01 | 2024-03-29 | 2024-04-01 | 2024-04-01 | KT Completed. In Steady State.
ProjectName_05 | James | William | Team 5 | 6 | 1 | 5 | 2024-02-07 | 2024-05-06 | 6 | 6 | 6 | 6 | 2024-03-19 | 2024-04-05 | 2024-05-06 | 2024-05-07 | 2024-05-21 | KT Completed. In Steady State. | Incumbent disengagement date changed to 6/28 to accommodate release schedule planned to be performed by incumbent, however steady state is negotiated to begin from 5/7 for TechM.